## README
PERT + Crashing Analysis Tool
OPSMGT 357 — ANZ Analytics Innovation Conference (2026)
How to use this workbook
1. Inputs sheet | Task data is already filled in from the case. The yellow column 'Crash Days Applied' is your control. Set values 0 to Max Crash for each task to test scenarios.
2. Network Paths sheet | Lists all 5 paths from start to finish. Each path's length and variance recalculates from Inputs. Critical path is auto-highlighted (the longest one).
3. Project Summary sheet | Shows current project duration, direct cost, indirect cost, total cost, and probability of finishing by your target date. Set the target on this sheet.
4. Crashing Log sheet | Use this to record your crashing decisions step by step for Scenarios 1, 2, 3. Each row = 1 crash decision.
5. Cost-Time Tradeoff sheet | After running crashing analysis, fill in this table to plot the cost vs duration curve (for Scenario 2).
6. Scenario Notes sheet | Brief reminders of what each scenario asks. Use this as your checklist.
Color conventions
Yellow cells with blue text | Inputs you can change.
Black text | Formulas — do not type over these.
Green text | Links pulling values from another sheet.
Red highlight | Critical path or warning.
Green highlight | Result / output cell.
Important conventions (from case study)
Expected Time | Rounded UP to nearest whole day (conservative).
Standard Deviation | Rounded to 1 decimal.
Indirect Cost | $4,200 per day saved. Original plan = $90,000 total.
What this tool does NOT do for you
• Identify which crashing strategy is optimal — you must reason through it.
• Decide whether the 45-day deadline is feasible — you must interpret results.
• Write the literature review, recommendations, or report.
• Verify your own arithmetic — always cross-check with hand calculations.
Suggested workflow for your group of 4
Step 1 (together) | Verify baseline: keep all 'Crash Days Applied' = 0. Confirm CP duration = 46 days. Each person hand-verifies a few rows.
Step 2 (Scenario 1) | Crash critical path tasks until P(≤45 days) ≥ 95%. Log each step in Crashing Log.
Step 3 (Scenario 2) | Continue crashing one cheapest day at a time. Build Cost-Time table. Find minimum total cost.
Step 4 (Scenario 3) | Crash everything possible. Record min duration + total cost.
Step 5 (Scenarios 4 & 5) | Modify Task 4 ET (subtract 7, set Max Crash to 0) for Scenario 4. For Scenario 5, change Task 8 Max Crash from 2 to 5. Re-run analysis.
Step 6 (write-up) | Each person drafts their assigned section. D-person integrates.

## Inputs
Task Inputs — ANZ Analytics Innovation Conference
Modify the YELLOW 'Crash Days Applied' column to test scenarios. All other columns auto-calculate.
Task ID | Task Name | Predecessors | a | m | b | ET (rounded up) | σ (1 dp) | σ² (Variance) | Normal Cost ($) | Max Crash (days) | Crash $/day | Crash Days Applied | Crashed Duration | Crash Cost ($)
1 | Initial Project Kick-Off | — | 1 | 2 | 3 | 2 | 0.3 | 0.09 | 3000 | 0 | — | 0 | 2 | 0
2 | Define Conference Themes & Tracks | 1 | 4 | 6 | 10 | 7 | 1 | 1 | 8000 | 2 | 4000 | 2 | 5 | 8000
3 | Keynote Speaker Identification | 1 | 3 | 6 | 12 | 7 | 1.5 | 2.25 | 10000 | 2 | 5000 | 2 | 5 | 10000
4 | Venue Booking & Contracting | 1 | 5 | 8 | 14 | 9 | 1.5 | 2.25 | 18000 | 3 | 6000 | 3 | 6 | 18000
5 | Hybrid Technical Setup | 4 | 6 | 10 | 16 | 11 | 1.7 | 2.89 | 22000 | 3 | 7000 | 3 | 8 | 21000
6 | Sponsorship Package Development | 2 | 3 | 5 | 9 | 6 | 1 | 1 | 6000 | 1 | 3000 | 1 | 5 | 3000
7 | Sponsor Outreach & Negotiation | 6 | 5 | 9 | 18 | 10 | 2.2 | 4.84 | 12000 | 3 | 4000 | 3 | 7 | 12000
8 | Keynote Speaker Confirmation | 3 | 4 | 7 | 13 | 8 | 1.5 | 2.25 | 14000 | 2 | 6000 | 2 | 6 | 12000
9 | Marketing Plan Development | 2, 8 | 4 | 7 | 11 | 8 | 1.2 | 1.44 | 9000 | 1 | 4000 | 1 | 7 | 4000
10 | Promotional Campaign Execution | 9 | 7 | 12 | 20 | 13 | 2.2 | 4.84 | 15000 | 3 | 5000 | 3 | 10 | 15000
11 | Catering & Layout Planning | 4 | 6 | 9 | 14 | 10 | 1.3 | 1.69 | 11000 | 2 | 4000 | 2 | 8 | 8000
12 | Volunteer Recruitment & Training | 11 | 4 | 7 | 13 | 8 | 1.5 | 2.25 | 8000 | 2 | 3500 | 2 | 6 | 7000
13 | On-Site Logistics Preparation | 5, 7, 12 | 5 | 9 | 15 | 10 | 1.7 | 2.89 | 20000 | 3 | 6000 | 3 | 7 | 18000
14 | Conference Delivery Day | 13, 10 | 1 | 1 | 1 | 1 | 0 | 0 | 30000 | 0 | — | 0 | 1 | 0
15 | Post-Event Feedback & Reporting | 14 | 3 | 5 | 8 | 6 | 0.8 | 0.64 | 6000 | 1 | 2000 | 1 | 5 | 2000
| TOTALS | [6 empty] | Direct cost → | 192000 |  |  |  | Crash cost → | 138000
[8 empty] | TOTAL DIRECT COST → | 330000

## Network Paths
Network Paths & Critical Path Identification
All 5 paths from start (Task 1) to finish (Task 15). Path length = sum of crashed durations along that path. Critical path = the longest one.
Path | Route | T1 | T2 | T3 | T4 | T5 | T6 | T7 | T8 | T9 | T10 | T11 | T12 | T13 | T14 | T15 | Length (days) | Variance | Std Dev | Critical?
Path A | 1→2→6→7→13→14→15 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 32 | 10.46 | 3.2342
Path B | 1→2→9→10→14→15 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 30 | 8.01 | 2.8302
Path C | 1→3→8→9→10→14→15 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 36 | 11.51 | 3.3926 | CRITICAL
Path D | 1→4→5→13→14→15 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 29 | 8.76 | 2.9597
Path E | 1→4→11→12→13→14→15 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 35 | 9.81 | 3.1321
Project Duration (Critical Path): |  |  | 36
Critical Path Variance (max-variance critical path): |  |  | 11.51
Critical Path Std Dev: |  |  | 3.3926

## Project Summary
Project Summary — Duration, Cost, Probability
All values update automatically when you change Crash Days Applied in the Inputs sheet.
INPUTS
Target Project Duration (days) | 45 | ← Change to test probability of finishing by other dates
Baseline Project Duration (days) | 46 | ← Original CP duration (set Crash Days = 0 and read from Network Paths)
Indirect Cost per Day Saved ($) | 4200
Total Indirect Cost (baseline) | 90000
CURRENT PROJECT STATE
Current Project Duration (days) | 36
Critical Path Variance | 11.51
Critical Path Std Dev | 3.3926
PROBABILITY ANALYSIS
Z-value = (Target − CP Duration) / σ_CP | 2.6528
P(Project ≤ Target Days) | 99.6%
↑ If this is below 95% for Scenario 1, you need more crashing.
COST ANALYSIS
Total Normal Direct Cost | 192000
Total Crash Cost Applied | 138000
TOTAL DIRECT COST | 330000
Days Saved (vs baseline) | 10
Indirect Cost Saved | 42000
Current Indirect Cost | 48000
TOTAL PROJECT COST (Direct + Indirect) | 378000

## Crashing Log
Crashing Decision Log
Record your step-by-step crashing decisions here. Use one row per crash step. At each step: identify the cheapest crashable task on the critical path, crash it 1 day, and check the new state in Project Summary.
Reminders for crashing logic:
1. Only crash tasks that are ON the critical path.
2. If multiple paths are critical, you may need to crash one task on EACH critical path that day (or one task that is on multiple critical paths).
3. Always pick the cheapest $/day option among eligible tasks.
4. Stop crashing when: (a) target probability reached, (b) all critical-path tasks at max crash, or (c) marginal cost of crashing > $4,200 (indirect savings).
5. Record each step below so you can write it up in your report.
Step | Task Crashed | Days Crashed (this step) | Crash $/day | Step Cost | Cumulative Crash Cost | New CP Duration | P(≤ target)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## Cost-Time Tradeoff
Cost–Time Tradeoff Table (for Scenario 2)
Fill this in as you crash. For each project duration achievable, record the direct and indirect costs. Total cost minimum = optimum point.
Project Duration (days) | Cumulative Crash Cost ($) | Total Direct Cost ($) | Indirect Cost ($) | Total Cost ($) | Notes
46 |  | 192000 | 90000 | 282000
45 |  | 192000 | 85800 | 277800
44 |  | 192000 | 81600 | 273600
43 |  | 192000 | 77400 | 269400
42 |  | 192000 | 73200 | 265200
41 |  | 192000 | 69000 | 261000
40 |  | 192000 | 64800 | 256800
39 |  | 192000 | 60600 | 252600
38 |  | 192000 | 56400 | 248400
37 |  | 192000 | 52200 | 244200
36 |  | 192000 | 48000 | 240000
35 |  | 192000 | 43800 | 235800
34 |  | 192000 | 39600 | 231600
Minimum Total Cost: |  |  |  | 231600
Optimum Project Duration (days): |  |  |  | 34

## Scenario Notes
Scenario Analysis Guide
Reminder of what each scenario asks. Tick off as you complete.
Baseline
What to do: | Set all Crash Days Applied = 0 in Inputs sheet.
Report deliverable: | Expected CP duration ≈ 46 days. P(≤45) ≈ 37%. This is your starting point.
Scenario 1: 95% confidence in 45 days
What to do: | Crash critical-path tasks (cheapest $/day first) until P(≤45 days) in Project Summary ≥ 95%.
Report deliverable: | Report: (a) which tasks crashed, (b) days each crashed, (c) total crash cost, (d) new ET and probability, (e) whether 45 days is realistic.
Scenario 2: Cost–Time Optimum
What to do: | From baseline, crash one day at a time. After each crash, check if marginal crash cost < $4,200 indirect savings. Continue until marginal crash cost > $4,200. Fill Cost-Time Tradeoff sheet.
Report deliverable: | Report: (a) optimum duration, (b) minimum total cost, (c) which tasks crashed and by how much, (d) graph (you can chart Cost-Time Tradeoff sheet).
Scenario 3: Minimum Duration
What to do: | Crash every eligible task by its max amount (set Crash Days Applied = Max Crash for tasks with crash capacity).
Report deliverable: | Report: (a) min possible duration, (b) total direct cost, (c) total indirect cost, (d) total cost, (e) cost-benefit judgment.
Scenario 4: Task 4 reduced by 7 days, no crash
What to do: | In Inputs: override Task 4 ET by editing a/m/b so ET drops by 7 (or temporarily hard-code Crashed Duration = original ET − 7 via Crash Days Applied = 7, and treat crash cost as 0 by NOT including it; simplest is to override Crash Days Applied = 7 and set Crash $/day to 0 temporarily). Then re-check critical path.
Report deliverable: | Report: (a) new network and CP, (b) does optimum point change, (c) is 45-day target now easier?
Scenario 5: Task 8 can be crashed 3 more days
What to do: | In Inputs: change Task 8 Max Crash from 2 to 5. Crash cost per day stays the same.
Report deliverable: | Report: (a) new optimum duration, (b) new min total cost, (c) does CP change, (d) impact on 45-day target.